## Sprint 1 - Planning
ID | Type | User Story | Acceptance Criteria | Priority (MoSCoW) | Story Points | Co-Owner | Owner(s) | Status | Notes
US1 | Feature | As a user, I want to write and submit a journal entry so that I can reflect on my daily emotions. | Text input available; Submit works; No empty submission | Must | 3 | Rafaela | Vanessa | To Do | Frontend form
US2 | Feature | As a user, I want my journal entry to be processed after submission so that I can receive emotional analysis. | Entry sent to backend successfully; No submission errors | Must | 5 | Chintan | Rafaela | To Do | API connection
US3 | Feature | As a user, I want my journal entry analyzed by AI so that I understand whether my emotional tone is positive, neutral, or negative. | Backend sends text to model; Sentiment label returned | Must | 8 | Sanket | Krishna | To Do | DistilBERT integration
US4 | Feature | As a user, I want to see how confident the system is in its prediction so that I can better interpret the result. | Confidence score extracted and returned | Should | 2 | Sanket | Krishna | To Do | Probability score
US5 | Feature | As a user, I want to see my sentiment result immediately after submission so that I receive instant feedback. | Sentiment + confidence displayed; No page reload | Could | 3 | Vanessa | Sanket | To Do | UI display
US6 | Feature | As a user, I want to see a simple visualization of my mood history so that I can begin identifying patterns. | Simple chart renders; Updates after submission | Should | 5 | Krishna | Rafaela | To Do | Basic chart
US7 | Feature | As a user, I want input validation so that my journal entries follow length and character rules. | Max length enforced; Allowed characters checked; No empty submissions | Must | 2 | Vanessa | Rafaela | To Do
US8 | Feature | As a user, I want a confirmation message when my entry is submitted so that I know it was received. | Submission confirmation displayed in UI | Must | 2 | Chintan | Sanket | To Do
US9 | Feature | As a user, I want to see friendly error messages if submission or analysis fails so that I understand what went wrong. | Backend/model errors caught; Clear error displayed | Could | 2 | Krishna | Chintan | To Do
US10 | Feature | As a user, I want the input field to reset after submission so that I can write a new entry easily. | Input cleared after successful submission | Must | 1 |  |  | To Do
US11 | Feature | As a user, I want to register an account so that my journal entries are securely stored | Email & password required, Password hashed, User saved in database, Duplicate email prevented | Will Not Have | 5 | Rafaela | Chintan | To Do
US12 | Feature | As a user, I want to log in so that I can access my journal dashboard. | JWT token generated, Protected routes enforced, Login eroor handling | Will Not Have | 5 | Rafaela | Chintan | To Do
US13 | Feature | As a user, I want to view my previous journal entries so that I can reflect on past emotional states | List view of entries, Emotion label shown, Sorted by date | Should | 8 | Vanessa | Chintan | To Do
TASK-R1 | Process | Prepare for retrospective | Gather metrics & blockers
TASK-R2 | Process | Conduct Sprint 1 Retrospective and document action items. | Meeting completed; Notes documented | [5 empty] | End of sprint
TASK-R3 | Process | Prepare Sprint Planning 2 | Gather metrics & user stories
Sprint Name | Sprint 1 |  |  | Total Story Points Committed | 51
Sprint Duration | February 20th, 2026 - March , 2026
Sprint Length | 3 Weeks
Sprint Goal | Deliver functional journal submission with sentiment analysis and basic visualization

## Task Breakdown - Final 1
Parent Story | Technical Task | Owner | Status | Estimated Hours
US1 | Design journal input form | Vanessa | To Do | 3 | TOTAL HOURS | 78.5
US1 | Implement submit function | Rafaela | To Do | 2
US1 | Add form validation (no empty submission, max length, allowed characters) | Rafaela | To Do | 2
US2 | Set up backend endpoint for journal entries | Rafaela | To Do | 2 | Owner | Sum of Estimated Hours
US2 | Connect frontend to backend endpoint | Rafaela | To Do | 1 | Chintan | 16.5
US2 | Test submission with dummy data | Chintan | To Do | 1 | Krishna | 23
US3 | Reserch/test DistilBERT sentiment pipeline | Krishna | To Do | 3 | Rafaela | 17.5
US3 | Install Hugging face transformers | Sanket | To Do | 1 | Sanket | 11.5
US3 | Implement sentiment service function | Sanket | To Do | 2.5 | Vanessa | 10
US3 | Map model output to: Positive / Neutral / Negative | Krishna | To Do | 5 | (blank)
US3 | Extract confidence score | Krishna | To Do | 3 | Grand Total | 78.5
US3 | Integrate model in POST/journal flow | Sanket | To Do | 3
US3 | Store sentiment + confidence in DB | Sanket | To Do | 4
US3 | Unit test model integration | Krishna | To Do | 2
US3 | Fine-tune / adapt model for journal data | Krishna | To Do | 4
US4 | Extract confidence probability from model | Krishna | To Do | 1
US5 | Display sentiment label in UI | Vanessa | To Do | 1
US5 | Display confidence score | Vanessa | To Do | 1
US5 | Prevent page relod | Sanket | To Do | 1
US5 | Test UI + Backend response | Chintan | To Do | 1
US6 | Install chart library | Rafaela | To Do | 3
US6 | Aggregate sentiment counts | Krishna | To Do | 3
US6 | Implement basic bar chart | Rafaela | To Do | 2
US6 | Update chart after new submission | Rafaela | To Do | 2
US6 | Test chart updates | Chintan | To Do | 1
US7 | Add frontend validation | Vanessa | To Do | 2
US7 | Add backend validation (Pydantic) | Rafaela | To Do | 2
US7 | Display validation error messages UI | Vanessa | To Do | 1
US7 | Display validation error messages | Rafaela | To Do | 1
US8 | Show success toast/message | Chintan | To Do | 1
US9 | Handle backend exceptions | Chintan | To Do | 2
US9 | Handle AI model failure | Krishna | To Do | 2
US9 | Handle network errors in frontend | Chintan | To Do | 1
US9 | Display friednly UI error messages | Chintan | To Do | 1.5
US10 | Clear textarea after successful submit | Rafaela | To Do | 0.5
US11 | Design User schema (mongodb)
US11 | Implement password hashing
US11 | Create POST/register endpoint
US11 | Prevent duplicate email registration
US11 | Text registration via Postman
US11 | Build frontend registration form
US11 | Connect frontend to backend endpoint
US11 | Display friednly error messages
US12 | Implement JWT token generation
US12 | Create post/login endpoint
US12 | Protect journal routes with JWT
US12 | Store token in frontend
US12 | Implement protected routes in React
US12 | Test authentication flow
US13 | Create GET/journal endpoint | Chintan | To Do | 3
US13 | Filter entries by logged-in user
US13 | Sort entries by date | Chintan | To Do | 2
US13 | Build journal history UI list | Vanessa | To Do | 2
US13 | Display sentiment tag per entry | Chintan | To Do | 2
US13 | Test retrieval flow | Chintan | To Do | 1
TASK-R1 | Prepare for retrospective
TASK-R2 | Conduct retrospective

## Task Breakdown
Parent Story | Technical Task | Owner | Status | Estimated Hours
US1 | Design journal input form |  | To Do |  | TOTAL HOURS | 0
US1 | Implement submit function
US1 | Add form validation (no empty submission, max length, allowed characters)
US2 | Set up backend endpoint for journal entries
US2 | Connect frontend to backend endpoint
US2 | Test submission with dummy data
US3 | Research/test DistilBERT model
US3 | Fine-tune / adapt model for journal data
US3 | Integrate DistilBERT model in backend
US3 | Unit test model integration
US4 | Extract confidence probability from model
US5 | Display sentiment and confidence in UI
US5 | Test UI integration with backend
US6 | Implement basic bar chart visualization
US6 | Update chart after submission
US8 | Show submission confirmation message
US9 | Implement error handling for submission/model failure
US10 | Reset input field after submission
TASK-R1 | Prepare for retrospective
TASK-R2 | Conduct retrospective

## Sprint 1 - Chintan
ID | Type | User Story | Acceptance Criteria | Priority (MoSCoW) | Story Points | Owner(s) | Status | Notes
US1 | Feature | As a user, I want to write and submit a journal entry so that I can reflect on my daily emotions. | Text input available; Submit works; No empty submission |  |  |  |  | Frontend form
US2 | Feature | As a user, I want my submitted journal entry to be analyzed by AI so that i understand whether my emotional tone is positive, neutral or negative | Backend receives text, Text send to DistilBERT, Sentiment label returned, Label stored in database |  | 8 |  |  | API connection
US3 | Feature | As a user, I want my journal entry analyzed by AI so that I understand whether my emotional tone is positive, neutral, or negative. | Backend sends text to model; Sentiment label returned |  |  |  |  | DistilBERT integration
US4 | Feature | As a user, I want to see how confident the system is in its prediction so that I can better interpret the result. | Confidence score extracted and returned |  |  |  |  | Probability score
US5 | Feature | As a user, I want to see my sentiment result immediately after submission so that I receive instant feedback. | Sentiment + confidence displayed; No page reload |  |  |  |  | UI display
US6 | Feature | As a user, I want to see a simple visualization of my mood history so that I can begin identifying patterns. | Simple chart renders; Updates after submission |  |  |  |  | Basic chart
US7 | Feature | As a user, I want input validation so that my journal entries follow length and character rules. | Max length enforced; Allowed characters checked; No empty submissions
US8 | Feature | As a user, I want a confirmation message when my entry is submitted so that I know it was received. | Submission confirmation displayed in UI
US9 | Feature | As a user, I want to see friendly error messages if submission or analysis fails so that I understand what went wrong. | Backend/model errors caught; Clear error displayed
US10 | Feature | As a user, I want the input field to reset after submission so that I can write a new entry easily. | Input cleared after successful submission
US11 | Feature | As a user, I want to register an account so that my journal entries are securely stored | Email & password required, Password hashed, User saved in database, Duplicate email prevented |  | 5
US12 | Feature | As a user, I want to log in so that I can access my journal dashboard. | JWT token generated, Protected routes enforced, Login eroor handling |  | 5
US13 | Feature | As a user, I want to view my previous journal entries so that I can reflect on past emotional states | List view of entries, Emotion label shown, Sorted by date |  | 5
TASK-R1 | Process | Prepare for retrospective | Gather metrics & blockers
TASK-R2 | Process | Conduct Sprint 1 Retrospective and document action items. | Meeting completed; Notes documented |  |  |  |  | End of sprint
TASK-R3 | Process | Prepare Sprint Planning 2 | Gather metrics & user stories
Sprint Name | Sprint 1 |  |  | Total Story Points Committed | 23
Sprint Duration | February 20th, 2026 - March , 2026
Sprint Length | 2 Weeks
Sprint Goal | Deliver functional journal submission with sentiment analysis and basic visualization